## Slide 1: People
UGent
  Student: Lance De Waele : lancedewaele@icloud.com
  Professor: Hiep Luong hiep.luong@ugent.be and Jan Aelterman Jan.Aelterman@ugent.be
RMA
  MarLand: Tien-Thanh Nguyen tien.thanh@eu4m.eu
  MarSur: Benoit Pairet Benoit.Pairet@mil.be
  VR – SLAM: Charles Hamesse Charles.Hamesse@mil.be

## Slide 2: Timeline
Master thesis:
  Oct 2021 – end of May 2022
  Midterm presentation in November – January (!?)
    22nd Oct: work plan
    9th June: submit thesis
    29 June or 1st July: thesis defense
  December – January: exam time
Project
  Data acquisition: planned for October (TBC)
    ZED Mini: IMU, Stereo cameras
    Data acquisition hardware: mid October (integrate with MarSur USV ?)
  Problem formulation, workplan, [literature study]: 22nd October
  Required skills (Python, Pytorch, RNN, time-series analysis …): January
  Work on problem: March
  Writing thesis: May

## Slide 3: Motivation
Estimate and predict the ship motion from IMU – and stereo vision
  MarLand:
    Define the optimum moment for the drones to land on the ship
      Less impact on the drone
  MarSur (!?):
    Stabilize the sensor inputs
      Filter out the ship movement
    Horizon detection, could be used for control USV
State prediction problem
  Given current states (and states in the past): IMU data
  Given latent space (images) of future action/input: images of incoming waves
  Predict the states in future
  Stock market example

## Slide 4: Problem
Inputs:
  Sequence of IMU data + stereo images in the timeframe (t-∆t_1,t)
    Other sensor maybe used – wind sensor, thrust of the USV
Output
  Ship motion: altitude (z), roll, pitch, yaw (angles and angular velocities) in the time (t, t+∆t_2)
Challenges:
  Estimation + prediction for time series sequences (visual features: water/waves)
  Define ∆t_1 and ∆t_2
  Realtime

## Slide 5: Way of Working
Bi-weekly meeting with small presentation
  Status/Result of given tasks (from previous meeting)
  Issues
  Plan for next 2 weeks
2 tasks will be given after each meeting
Use Slack as communication channel
  New ideas
  Issues
  Q&A